## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Bryce | 8300 | 3850 | 4450 | 5200 | 600 | 4600 | 2000 | 850 | 1150 | 1100 | 2400 | -1300
Carson | 8200 | 4150 | 4050 | 4300 | 700 | 3600 | 2000 | 850 | 1150 | 1900 | 2600 | -700
Tosin | 6500 | 1050 | 5450 | 4000 | 0 | 4000 | 2000 | 250 | 1750 | 500 | 800 | -300
Marissa | 5600 | 3550 | 2050 | 2500 | 700 | 1800 | 2000 | 850 | 1150 | 1100 | 2000 | -900
Molly | 9900 | 3925 | 5975 | 6700 | 375 | 6325 | 2000 | 850 | 1150 | 1200 | 2700 | -1500
Ambrea | 5800 | 1850 | 3950 | 2900 | 100 | 2800 | 2000 | 350 | 1650 | 900 | 1400 | -500
Total | 44300 | 18375 | 25925 | 25600 | 2475 | 23125 | 12000 | 4000 | 8000 | 6700 | 11900 | -5200

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned |  |  | Slack
Bryce |  |  | hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
Sprite creation | 1 | 3
Character artwork & animations | 20 | 0
Movement | 3 | 3
Melee | 5 | 0
Animation controler | 3 | 0
Weapon sprite holder creation | 2 | 0
bullet creation | 4 | 0
Bullet interaction | 6 | 0
Weapon invintory system | 5 | 0
Reload animation and invintory inplementation | 3 | 0
totals | 52 | 6
Carson
1- GameManager Layout | 4 | 4
2- Basic Map Creation | 2 | 1
3- Enemy Spawning Algorithm | 6 | 1 | [5 empty] | 2022-01-02
4- Map Refinement | 4 | 0 | [5 empty] | 2022-01-02
5- MapManager Script Creation | 8 | 1
6- Room Layout and Scripts | 6 | 0 | [9 empty] | 2022-04-05
7- Testing | 8 | 0 | [15 empty] | 2022-03-06
8- Export Final Product | 2 | 0 | [23 empty] | 7
9- Documentation | 3 | 0 | [25 empty] | 8
totals | 43 | 7
Tosin
1. Acquire Sprites and Assets | 2 | 0
2. Animation | 20 | 0 |  |  |  | 1
3. Scripting | 15 | 0 | [5 empty] | 2
4. Testing | 3 | 0 | [20 empty] | 3
| 0 | 0
| 0 | [19 empty] | `
| 0 | 0
totals | 40 | 0
Marissa
Research sounds | 1 | 2
Download and upload sounds | 2 | 1 |  |  | 1
add sounds to sound manager and audio source | 5 | 3 |  |  |  |  | 2
Design item sprites | 1 | 0
Create randomizer functions | 5 | 0 | [10 empty] | 3,4
User Documnetation | 6 | 1 | [15 empty] | 5
Testing | 4 | 0 | [21 empty] | 6
Installation | 1 | 0 | [25 empty] | 7
totals | 25 | 7
Molly
Create Sprite | 3 | 0.25
Create Dog Class | 1 | 1
Create Zombie Dog Subclass | 1 | 2 | [5 empty] | 2
Animation | 20 | 0.5
Sprite Attack | 6 | 0 | [24 empty] | 3,4
Sprite Damage | 5 | 0 | [24 empty] | 3,4
Death Processes | 10 | 0 | [29 empty] | 6
Leveling Difficulty | 3 | 0 | [39 empty] | 5,7
Sprite AI | 10 | 0 | [42 empty] | 8
Documentation | 2 | 0 | [52 empty] | 9
Testing | 6 | 0 | [54 empty] | 10
totals | 67 | 3.75
Ambrea
Research Inventory | 3 | 1
Create UIs | 4 | 0 |  |  |  |  | 1
Make user interact w/inventory | 6 | 0 | [8 empty] | 2
Make item interact w/inventory | 6 | 0 | [8 empty] | 2
Test UI's | 4 | 0 | [14 empty] | 3,4
Finalize | 6 | 0 | [18 empty] | 5
totals | 29 | 1
group totals (hrs) | 256 | 24.75
group totals ($) | 25600 | 2475

## Meetings
| Date | Aug. 30 | Sept. 11 | Sept. | Sept. 19 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Meeting about features | Meeting about roles & documents | Worked On final SA presentation | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 2 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bryce | 8.5 | 1 | 2 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carson | 8.5 | 1 | 2 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tosin | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marissa | 8.5 | 1 | 2 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Molly | 8.5 | 1 | 2 | 0.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ambrea | 3.5 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 40 | 6 | 11 | 3 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SA
bingus | Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Bryce
| Class Diagram | 2 | 3 | bar: 1 to 3
| Sequence Diagram | 1 | 1 | bar: 4
| Use Case | 1 | 3 | bar: 5 to 7
| Diagram 0/Level 1 | 1 | 3 | bar: 8 to 10
| SA Presentation | 2 | 5 | bar: 11 to 15
| RFP - Current systems | 2 | 5 | bar: 16 to 20
| Pert & GanttChart | 2 | 4 | bar: 21 to 24
| Subtotal | 11 | 24
Carson
| Champion use cases | 2 | 2 | bar: 1 to 2
| Champion DFD+processes | 2 | 3 | bar: 3 to 5
| Champion scenarios | 1 | 2 | bar: 6 to 7
| Champion acceptance tests | 2 | 2 | bar: 8 to 9
| Champion timeline+charts | 2 | 2 | bar: 10 to 11
| SA Presentation Class Diagram | 2 | 4 | bar: 12 to 15
| SA Presentaion Sequence Diagram | 1 | 1 | bar: 16
| RFP Constraints | 2 | 1 | bar: 17
| RFP Schedule | 1 | 1 | bar: 18
| SA Presentation Storyboard | 3 | 6 | bar: 19 to 24
| SA Presentation Subsystem | 1 | 2 | bar: 25 to 26
bingus | Subtotal | 19 | 26
Tosin
| Class Diagram | 2 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 2 | bar: 3 to 4
| Use Case | 1 | 3 | bar: 5 to 7
| RFP - Known interactions/ Glossary | 1 | 1 | bar: 8
| Data flow diagram | 1 | 2 | bar: 9 to 10
| Champion document | 2 | 6 | bar: 11 to 16
| SA Presentation | 1 | 1 | bar: 17
| Subtotal | 5 | 8
Marissa
| Class Diagram | 1 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 2 | bar: 3 to 4
| Use Case | 1 | 2 | bar: 5 to 6
| RFP - project objectives | 1 | 1 | bar: 7
| Data flow diagram | 1 | 3 | bar: 8 to 10
| Champion document | 1 | 4 | bar: 11 to 14
| SA presentation | 4 | 5 | bar: 15 to 19
| Storyboard | 1 | 1 | bar: 20
| Subtotal | 11 | 20
Molly
| Class Diagram | 1 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 3 | bar: 3 to 4
| Use Cases-Individual and Global | 1 | 3 | bar: 5 to 7
| DFDs-Individual and Global | 1 | 5 | bar: 8 to 12
| SA Presentation | 4 | 5 | bar: 13 to 17
| StoryBoard | 1 | 1 | bar: 18
| RFP-Problem Description/Editing | 1 | 1 | bar: 19
| Champion Document | 1 | 4 | bar: 20 to 23
| Pert and Gantt Chart | 1 | 3 | bar: 24 to 26
| Subtotal | 12 | 27
Ambrea
| Class Diagram | 1 | 4 | bar: 1 to 4
| Sequence Diagram | 1 | 1 | bar: 5
| Use Case | 1 | 2 | bar: 6 to 7
| RFP-4.0 | 1 | 1 | bar: 8
| Diagram Level 1 | 2 | 2 | bar: 9 to 10
| SA Presentation | 1 | 1 | bar: 11
| Champion Document | 3 | 6 | bar: 12 to 17
| Pert and Gantt Chart | 1 | 2 | bar: 18 to 19
| Subtotal | 9 | 14
| Total | 67 | 119