## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Bryce | 8200 | 9050 | -850 | 5100 | 5600 | -500 | 2000 | 1050 | 950 | 1100 | 2400 | -1300
Carson | 8900 | 13150 | -4250 | 5000 | 9500 | -4500 | 2000 | 1050 | 950 | 1900 | 2600 | -700
Tosin | 6500 | 5500 | 1000 | 4000 | 3800 | 200 | 2000 | 900 | 1100 | 500 | 800 | -300
Marissa | 5900 | 7250 | -1350 | 2800 | 4200 | -1400 | 2000 | 1050 | 950 | 1100 | 2000 | -900
Molly | 10300 | 11150 | -850 | 7100 | 7400 | -300 | 2000 | 1050 | 950 | 1200 | 2700 | -1500
Ambrea | 5800 | 1800 | 4000 | 2900 | 100 | 2800 | 2000 | 300 | 1700 | 900 | 1400 | -500
Total | 45600 | 47900 | -2300 | 26900 | 30600 | -3700 | 12000 | 5400 | 6600 | 6700 | 11900 | -5200

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned |  |  | Slack |  | Cancelled
Bryce |  |  | hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
Sprite creation | 1 | 3
Player Structure (Decorator pattern) | - | 4
Character artwork & animations | 20 | 6
Movement | 3 | 3
Weapon sprite holder creation | 2 | 2
bullet creation(object pool) | 4 | 7
Bullet interaction | 6 | 1
Weapon inventory system | 5 | 3
Reload and inventory inplementation | 3 | 3
Create drop interactions | 2 | 4
Testing | - | 10
Documentation | 5 | 10
totals | 51 | 56
Carson
1- GameManager Layout | 4 | 4
2- Basic Map Creation | 2 | 3
3- Enemy Spawning Algorithm | 8 | 13 | [5 empty] | 2022-01-02
3.5-HUD | 5 | 10
4- Map Refinement | 4 | 22 | [5 empty] | 2022-01-02
5- MapManager Script Creation | 7 | 8
6- Room Layout and Scripts | 6 | 15 | [9 empty] | 5
7- Testing | 8 | 9 | [18 empty] | 3
8- Export Final Product | 2 | 2 | [27 empty] | 2022-04-07
9- Documentation | 4 | 9 | [24 empty] | 3, 5, 6
totals | 50 | 95
Tosin
1. Acquire Sprites and Assets? | 2 | 2
2. Starting Cutscene Animation (Cam Panning) | 3 | 1 |  |  |  | 1
3. Cure Cutscene Animation (Ingredients are acquired) | 3 | 2 |  |  |  |  | 2
4.Final Cutscene Animation (End Scene) | 14 | 9 | [6 empty] | 3
5. Animation Trigger Scripting | 15 | 17 | [15 empty] | 4
6. Testing | 3 | 7 |  |  |  | 1
| 0 | 0
| 0 | 0 | [18 empty] | `
| 0 | 0
totals | 40 | 38
Marissa
1. Research sounds | 1 | 2
2. Download and upload sounds | 2 | 2 |  |  | 1
3. add sounds to sound manager and audio source | 5 | 3 |  |  |  |  | 2
4. Design item sprites | 1 | 3
5. Create randomizer functions | 5 | 16 | [10 empty] | 3,4
6. create object pool pattern for items | 3 | 4 | [15 empty] | 5
7. User Documentation | 6 | 6 | [18 empty] | 6
8. Testing | 4 | 5 | [24 empty] | 7
9. Installation | 1 | 1 | [28 empty] | 8
totals | 28 | 42
Molly
1. Create Sprite | 3 | 3
2. Create Dog Class | 1 | 1 |  |  |  |  | 1
3. Create Zombie Dog Subclass | 1 | 2 | [5 empty] | 2
4. Animation | 20 | 20 |  |  |  |  | 1
5. Sprite Attack | 6 | 6 | [24 empty] | 3,4
6. Sprite Damage | 5 | 6 | [24 empty] | 3,4
7. Death Processes | 10 | 11 | [29 empty] | 6
8. Leveling Difficulty/Decorator Pattern | 3 | 4 | [39 empty] | 5,7
9. Object Pooler Pattern | 10 | 10 | [42 empty] | 8
10. Boss Dog | 3 | 2 | [42 empty] | 9
11. Demo Mode (Dependent on Tosin's Cutscene = 5t?) | 1 | 1 | [52 empty] | 10, 5t
12. Documentation | 2 | 4 | [52 empty] | 11
13. Testing | 6 | 4 | [54 empty] | 12
totals | 71 | 74
Ambrea
Research Inventory | 3 | 1
Create UIs | 4 | 0 |  |  |  |  | 1
Make user interact w/inventory | 6 | 0 | [8 empty] | 2
Make item interact w/inventory | 6 | 0 | [8 empty] | 2
Test UI's | 4 | 0 | [14 empty] | 3,4
Finalize | 6 | 0 | [18 empty] | 5
totals | 29 | 1
group totals (hrs) | 269 | 306
group totals ($) | 26900 | 30600

## Meetings
| Date | Aug. 30 | Sept. 11 | Sept. 13 | Sept. 19 | 2022-10-21 | 2022-11-02 | 2022-11-09
| Purpose | First meeting in class | Meeting about features | Meeting about roles & documents | Worked On final SA presentation | Meeting about progress | Meeting about progress and talked about deadlines | Meeting to discuss final project | Meeting with BC | Presenting finished product
| Hours | 1 | 2 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Bryce | 10.5 | 1 | 2 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Carson | 10.5 | 1 | 2 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Tosin | 9 | 1 | 1 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0 | 0
Marissa | 10.5 | 1 | 2 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Molly | 10.5 | 1 | 2 | 0.5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Ambrea | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 54 | 6 | 11 | 2.5 | 25 | 2.5 | 2.5 | 2.5 | 2 | 0

## SA
bingus | Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Bryce
| Class Diagram | 2 | 3 | bar: 1 to 3
| Sequence Diagram | 1 | 1 | bar: 4
| Use Case | 1 | 3 | bar: 5 to 7
| Diagram 0/Level 1 | 1 | 3 | bar: 8 to 10
| SA Presentation | 2 | 5 | bar: 11 to 15
| RFP - Current systems | 2 | 5 | bar: 16 to 20
| Pert & GanttChart | 2 | 4 | bar: 21 to 24
| Subtotal | 11 | 24
Carson
| Champion use cases | 2 | 2 | bar: 1 to 2
| Champion DFD+processes | 2 | 3 | bar: 3 to 5
| Champion scenarios | 1 | 2 | bar: 6 to 7
| Champion acceptance tests | 2 | 2 | bar: 8 to 9
| Champion timeline+charts | 2 | 2 | bar: 10 to 11
| SA Presentation Class Diagram | 2 | 4 | bar: 12 to 15
| SA Presentaion Sequence Diagram | 1 | 1 | bar: 16
| RFP Constraints | 2 | 1 | bar: 17
| RFP Schedule | 1 | 1 | bar: 18
| SA Presentation Storyboard | 3 | 6 | bar: 19 to 24
| SA Presentation Subsystem | 1 | 2 | bar: 25 to 26
bingus | Subtotal | 19 | 26
Tosin
| Class Diagram | 2 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 2 | bar: 3 to 4
| Use Case | 1 | 3 | bar: 5 to 7
| RFP - Known interactions/ Glossary | 1 | 1 | bar: 8
| Data flow diagram | 1 | 2 | bar: 9 to 10
| Champion document | 2 | 6 | bar: 11 to 16
| SA Presentation | 1 | 1 | bar: 17
| Subtotal | 5 | 8
Marissa
| Class Diagram | 1 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 2 | bar: 3 to 4
| Use Case | 1 | 2 | bar: 5 to 6
| RFP - project objectives | 1 | 1 | bar: 7
| Data flow diagram | 1 | 3 | bar: 8 to 10
| Champion document | 1 | 4 | bar: 11 to 14
| SA presentation | 4 | 5 | bar: 15 to 19
| Storyboard | 1 | 1 | bar: 20
| Subtotal | 11 | 20
Molly
| Class Diagram | 1 | 2 | bar: 1 to 2
| Sequence Diagram | 1 | 3 | bar: 3 to 4
| Use Cases-Individual and Global | 1 | 3 | bar: 5 to 7
| DFDs-Individual and Global | 1 | 5 | bar: 8 to 12
| SA Presentation | 4 | 5 | bar: 13 to 17
| StoryBoard | 1 | 1 | bar: 18
| RFP-Problem Description/Editing | 1 | 1 | bar: 19
| Champion Document | 1 | 4 | bar: 20 to 23
| Pert and Gantt Chart | 1 | 3 | bar: 24 to 26
| Subtotal | 12 | 27
Ambrea
| Class Diagram | 1 | 4 | bar: 1 to 4
| Sequence Diagram | 1 | 1 | bar: 5
| Use Case | 1 | 2 | bar: 6 to 7
| RFP-4.0 | 1 | 1 | bar: 8
| Diagram Level 1 | 2 | 2 | bar: 9 to 10
| SA Presentation | 1 | 1 | bar: 11
| Champion Document | 3 | 6 | bar: 12 to 17
| Pert and Gantt Chart | 1 | 2 | bar: 18 to 19
| Subtotal | 9 | 14
| Total | 67 | 119