## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Bryce | 6800 | 950 | 5850 | 5200 | 600 | 4600 | 1000 | 350 | 650 | 600 | 0 | 600
Carson | 9600 | 1850 | 7750 | 4300 | 700 | 3600 | 1000 | 450 | 550 | 4300 | 700 | 3600
Tosin | 9000 | 250 | 8750 | 4000 | 0 | 4000 | 1000 | 250 | 750 | 4000 | 0 | 4000
Marissa | 6900 | 450 | 6450 | 2500 | 0 | 2500 | 1000 | 450 | 550 | 3400 | 0 | 3400
Molly | 14300 | 700 | 13600 | 6600 | 125 | 6475 | 1000 | 450 | 550 | 6700 | 125 | 6575
Ambrea | 6100 | 450 | 5650 | 2900 | 100 | 2800 | 1000 | 350 | 650 | 2200 | 0 | 2200
Total | 52700 | 4650 | 48050 | 25500 | 1525 | 23975 | 6000 | 2300 | 3700 | 21200 | 825 | 20375

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned |  |  | Slack
Bryce |  |  | hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
Sprite creation | 1 | 3 | bar: 1
Character artwork & animations | 20 | 0 | bar: completed 2 to Slack 21
Movement | 3 | 3 | bar: completed 2 to Slack 21
Melee | 5 | 0 | bar: this week 5 to Slack 21
Animation controler | 3 | 0 | bar: Slack 22 to Slack 24
Weapon sprite holder creation | 2 | 0 | bar: completed 2 to Slack 24
bullet creation | 4 | 0 | bar: completed 4 to Slack 24
Bullet interaction | 6 | 0 | bar: planned 8 to Slack 24
Weapon invintory system | 5 | 0 | bar: planned 8 to Slack 24
Reload animation and invintory inplementation | 3 | 0 | bar: Slack 25 to Slack 27
totals | 52 | 6
Carson
1- GameManager Layout | 4 | 4 | bar: 1 to completed 4
2- Basic Map Creation | 2 | 1 | bar: 1 to completed 4
3- Enemy Spawning Algorithm | 6 | 1 |  | this week 5: 2022-01-02
4- Map Refinement | 4 | 0 |  | this week 5: 2022-01-02
5- MapManager Script Creation | 8 | 1 | bar: 1 to planned 8
6- Room Layout and Scripts | 6 | 0 |  | planned 9: 2022-04-05
7- Testing | 8 | 0 |  | Slack 15: 2022-03-06
8- Export Final Product | 2 | 0 |  | Slack 23: 7
9- Documentation | 3 | 0 |  | Slack 25: 8
totals | 43 | 7
Tosin
1. Acquire Sprites and Assets | 2 | 0 | bar: 1 to completed 2
2. Animation | 20 | 0 | bar: completed 3 to Slack 22
3. Scripting | 15 | 0 |  | this week 5: 2
4. Testing | 3 | 0 |  | Slack 20: 3
| 0 | 0
0 | bar: Slack 18
| 0 | 0
totals | 40 | 0
Marissa
Research sounds | 1 | 0 | bar: 1
Download and upload sounds | 2 | 0 | bar: completed 2 to completed 3
add sounds to sound manager and audio source | 5 | 0 |  | completed 4: 2
Design item sprites | 1 | 0 | bar: planned 9
Create randomizer functions | 5 | 0 |  | planned 10: 3,4
User Documnetation | 6 | 0 |  | Slack 15: 5
Testing | 4 |  |  | Slack 21: 6
Installation | 1 | 0 |  | Slack 25: 7
totals | 25 | 0
Molly
1 | 3 | 0.25 | bar: 1 to completed 3
2 | 1 | 0.5 | bar: completed 4 to Slack 22
3 | 1 | 0 |  | this week 5: 2
4 | 20 | 0.5 | bar: completed 4 to Slack 23
5 | 6 | 0 |  | Slack 24: 3,4
6 | 5 | 0 |  | Slack 24: 3,4
7 | 10 | 0 |  | Slack 29: 6
8 | 3 | 0 |  | Slack 39: 5,7
9 | 10 | 0 |  | Slack 42: 8
10 | 2 | 0 |  | Slack 52: 9
11 | 6 | 0 |  | Slack 54: 10
totals | 66 | 1.25
Ambrea
Research Inventory | 3 | 1 | bar: 1 to completed 3
Create UIs | 4 | 0 | bar: completed 4 to this week 7
Make user interact w/inventory | 6 | 0 |  | planned 8: 2
Make item interact w/inventory | 6 | 0 |  | planned 8: 2
Test UI's | 4 | 0 |  | Slack 14: 3,4
Finalize | 6 | 0 |  | Slack 18: 5
totals | 29 | 1
group totals (hrs) | 255 | 15.25
group totals ($) | 25500 | 1525

## Meetings
| Date | Aug. 30 | Sept. 11 | Sept. | Sept. 19 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Meeting about features | Meeting about roles & documents | Worked On SA presentation | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bryce | 3.5 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carson | 4.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tosin | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marissa | 4.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Molly | 4.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ambrea | 3.5 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 23 | 6 | 11 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Bryce
Sprite creation | 1 | 3 | bar: 1
Character artwork & animations | 20 | 0 | bar: 2 to 21
Movement | 3 | 3 | bar: 2 to 21
Melee | 5 | 0 | bar: 5 to 21
Animation controler | 3 | 0 | bar: 22 to 24
Weapon sprite holder creation | 2 | 0 | bar: 2 to 24
bullet creation | 4 | 0 | bar: 4 to 24
Bullet interaction | 6 | 0 | bar: 8 to 24
Weapon invintory system | 5 | 0 | bar: 8 to 24
Reload animation and invintory inplementation | 3 | 0 | bar: 25 to 27
| Subtotal | 6 | 0
Carson
| 1- GameManager Layout | 4 | 4 | bar: 1 to 4
| 2- Basic Map Creation | 2 | 1 | bar: 1 to 4
| 3- Enemy Spawning Algorithm | 6 | 1 | 5: 2022-01-02
| 4- Map Refinement | 4 | 0 | 5: 2022-01-02
| 5- MapManager Script Creation | 8 | 1 | bar: 1 to 8
| 6- Room Layout and Scripts | 6 | 0 | 9: 2022-04-05
| 7- Testing | 8 | 0 | 15: 2022-03-06
| 8- Export Final Product | 2 | 0 | 23: 7
| 9- Documentation | 3 | 0 | 25: 8
| Subtotal | 43 | 7
Tosin
|  | 2 | 0 | bar: 1 to 2
|  | 20 | 0 | bar: 3 to 22
|  | 15 | 0 | bar: 5 to 19
|  | 3 | 0 | bar: 20 to 22
| Subtotal | 40 | 0
Marissa
| 1 | 1 | bar: 1
| 2 | 2 | bar: 2 to 3
| 3 | 5 | bar: 4 to 8
| 4 | 1 | 0 | bar: 9
| 5 | 5 | bar: 10 to 14
| 6 | 6 | bar: 15 to 20
| 7 | 4 | bar: 21 to 24
| 8 | 10 | bar: 25
| Subtotal | 34 | 0
Molly
| 1 | 3 | 0.25 | bar: 1 to 3
| 2 | 1 | 0.5 | bar: 4 to 22
| 3 | 1 |  | 5: 2
| 4 | 20 | 0.5 | bar: 4 to 23
| 5 | 6 |  | 24: 3,4
| 6 | 5 |  | 24: 3,4
| 7 | 10 |  | 29: 6
| 8 | 3 | [31 empty] | 7
| 9 | 10 | [32 empty] | 8
| 10 | 2 | [33 empty] | 9
| 11 | 6 | [34 empty] | 10
| Subtotal | 67 | 1.25
Ambrea
|  | 3 | 1 | bar: 1 to 3
4 | bar: 4 to 7
|  | 6 |  | 8: 2
|  | 6 |  | 8: 2
|  | 4 |  | 14: 3,4
|  | 6 |  | 18: 5
| Subtotal | 22 | 0
| Total | 212 | 8.25